# FS Cloud Migration Plan

## VSI to OpenShift Migration – URL Preservation Strategy

Start Date: 16 February 2026

Q1 Milestone Target: 31 March 2026

Production Migration Target: Early April 2026

## 1. Executive Summary

This document describes the migration of CIDP/DXP environments from a Virtual Server Instance (VSI)-based architecture to OpenShift within FS Cloud. The objective is to migrate backend workloads while preserving existing public URLs, DNS entries, and Apigee base paths. The migration is infrastructure-only and does not include any functional or application release changes.

## 2. Current and Target Architecture

Current Architecture (VSI-Based):
- IBM Cloud CIS (WAF)
- Apigee API Gateway
- Backend services deployed on VSI

Target Architecture (OpenShift-Based):
- IBM Cloud CIS (unchanged)
- Apigee API Gateway (externally unchanged)
- Backend services deployed on OpenShift
- OpenShift routes replacing VSI targets

External hostnames and DNS entries remain unchanged.

## 3. Release Alignment Requirement

For each environment, the OpenShift deployment must use the exact same release version currently running on VSI. The image tag and artifact version must be verified before migration. No concurrent feature release is allowed during migration windows. A change freeze must be applied.

## 4. Validation Model

Validation is executed in parallel by HO (France) and LATAM teams and includes:
- URL reachability checks
- API validation (where applicable)
- Routing verification (CIS to Apigee to OpenShift)
- Log inspection
- Basic stability and smoke testing

## 5. Migration Planning by Environment

| Environment | Migration Date | Validation Window | Duration | Sign-off | Notes |
| --- | --- | --- | --- | --- | --- |
| APPP07 | Already migrated | 16–17 Feb | 2 days | 18 Feb | No API |
| APPP06 | 23 Feb | 24–25 Feb | 2 days | 26 Feb | Sandbox |
| APPP01 | 26 Feb | 27 Feb – 3 Mar | 3 days | 4 Mar | Standard |
| APPP03 | 4 Mar | 5–6 Mar | 2 days | 6 Mar | Standard |
| APPP04 | 9 Mar | 10–11 Mar | 2 days | 11 Mar | Standard |
| APPP05 | 11 Mar | 12–13 Mar | 2 days | 13 Mar | Standard |
| APPP02 (QA) | 16 Mar | 17–20 Mar | 5 days | 20 Mar | Complex |
| UAT | 23 Mar | 24–27 Mar | 5 days | 27 Mar | Business validation |
| STAGE | 30 Mar | 31 Mar | 2 days | 31 Mar | Smoke only |
| PROD | 6 Apr | 7–10 Apr | 5 days | 10 Apr | Governance window |

## 6. Service Mapping – VSI to OpenShift

| Environment | Current VSI Target | OpenShift Namespace | OpenShift Service | OpenShift Route | Status |
| --- | --- | --- | --- | --- | --- |
| APPP07 | vsi-app07.internal | ns-dev | svc-cidp | route-app07 | Migrated |
| APPP06 | vsi-app06.internal | ns-dev | svc-cidp | route-app06 | Planned |
| APPP01 | vsi-app01.internal | ns-dev | svc-cidp | route-app01 | Planned |
| APPP02 | vsi-app02.internal | ns-qa | svc-cidp | route-app02 | Planned |
| UAT | vsi-uat.internal | ns-uat | svc-cidp | route-uat | Planned |
| PROD | vsi-prod.internal | ns-prod | svc-cidp | route-prod | Planned |

## 7. Rollback Strategy

If any issue occurs after migration, Apigee target can be reverted to VSI. VSI infrastructure will remain available during the validation window. Migration is considered final only after formal sign-off.

## 8. Conclusion

All non-production environments will be migrated before the end of Q1 2026. Production migration is scheduled for early April 2026 under governance supervision. Strict release alignment and controlled validation are key success factors.